## Slide 1
Securing our Water Supply Future
City Leader Summit
April 2026

## Slide 2: Moderator Remarks: Councilmember Rudy Mendoza City of Woodlake

## Slide 3: Opening Remarks: Senator Melissa Hurtado California State Senate District 16

## Slide 4: Panelist: Jennifer Pierre Executive Director, State Water Contractors

## Slide 5: Panelist: Jerry Brown Executive Director, Sites Project Authority

## Slide 6: Sites Reservoir Project Update
April 23, 2026
Jerry Brown, Executive Director
Sites Project Authority

## Slide 7: What Problem Does the Sites Project Help Solve?
Excerpted from Aug 2022 “California’s Water Supply Strategy, Adapting to a Hotter Drier Future”

## Slide 8: General Project Update
Water Right – draft order issued March 19, 2026 and final by mid Sept 2026
Critical permits and approvals – ITP’s and BO (constr) received, 404/401 (wetlands) in progress, Sec 106/ROD complete
Construction Contractor Selections – underway
Land Acquisitions - ~ 90% of critical path project area acquired, TROEs being secured for enviro surveys
Engineering Design – completed to ~ 30% design, DSOD initial review complete (no red flags)
Cost Estimate and Schedule Update– cost updated in June 2025, schedule updated in January 2026
Financing – sources secured and loan agreements being negotiated
Off-Taker Contracts – in final negotiations
Notes: Jerry

## Slide 9: Sites Draft Water Right Permit was issued on 3/20/26 This is a major project milestone!
The draft permit finds water is available which confirms that Sites is a new water supply for California.
A permit of this magnitude for a new water supply has not occurred in decades and may not happen again.
Certain draft permit conditions may alter the project plans. Examples are:
  Additional diversion criteria and other limits on filling
  Uncertainties with the Bay Delta Plan Update
  Rights to local Creek water subject to further review
  Coordination to maintain South Delta water levels and quality when Sites water is exported
Sites Authority will be seeking changes in the permit prior to adoption in September 2026.

## Slide 10: Current Allocation of Active Sites Storage Space
Participant Name | Storage Allocation | % Available Storage
Antelope Valley-East Kern WA | 3,117 | 0.2%
City of American Canyon | 24,936 | 1.8%
Coachella Valley WD | 62,340 | 4.4%
Colusa County | 62,340 | 4.4%
Colusa County WD | 57,702 | 4.1%
Cortina WD | 2,805 | 0.2%
Davis WD | 12,468 | 0.9%
Desert WA | 40,521 | 2.9%
Dunnigan WD | 18,527 | 1.3%
Glenn-Colusa ID | 31,170 | 2.2%
Irvine Ranch WD | 6,234 | 0.4%
LaGrande WD | 6,234 | 0.4%
Metropolitan Water District of SC | 311,700 | 22.1%
Reclamation District 108 | 24,936 | 1.8%
Rosedale-Rio Bravo WD | 3,117 | 0.2%
San Bernardino Valley Municipal WD | 133,408 | 9.5%
San Gorgonio Pass WA | 87,276 | 6.2%
Santa Clara Valley WD | 3,117 9,351 | 0.2% 0.6%
Santa Clarita Valley WA | 31,170 | 2.2%
Westside WD | 33,508 | 2.4%
Wheeler Ridge - Maricopa WSD | 19,014 12,780 | 1.3% 0.9%
Zone 7 WA | 62,340 | 4.4%
State of California - Total | 244,000 | 17.3%
Reclamation | 128,020 | 9.1%
Available Storage Total | 1,410,000 | 100.0%
At a glance:
North of Delta – 19.4%
South of Delta – 53.9%
Reclamation – 9.1%
State Prop 1 – 17.3%
7
We do expect more shifts in capacity as Participants make final funding decisions.

## Slide 11: The Authority has a strategy for delivering the Project and managing risk Contracting Strategy adopted in July 2022
Sites Authority
Partner Facilities
Stand Alone and Specialty
Reservoir
Facilities
Conveyance Facilities
Hydraulics
Power
System Controls
O&M
Ownership
Operations
Logistics
Material Balance
Schedule
Community
Dunnigan Pipeline
Huffmaster Road
Reservoir Clearing
Recreation
Mitigation
CMAR Reservoir/Roads Awarded to Barnard on Jan 16, 2026
CMAR Conveyance – Procurement Coming in Spring 2026
2028 and Beyond
Design-Build Terrestrial Compensatory Mitigation RFQ/RFP Currently Out For Bid
Notes: 9 Packages

## Slide 12: The draft water right brings more clarity to the near-term decision schedule

## Slide 13: Timeline: Construction is on the Horizon
Sites Project Schedule (adopted January 2026)
Notes: Jerry

## Slide 14
”At $1.9B Diamond Valley Lake is a massive infrastructure investment. Questions raised whether costs justified.” (1991)
"California’s Bold Water Plan: $1.75 Billion State Water Project Sparks Debate on Cost and Feasibility" (May 10, 1960)
”Yuba County Voters Approved a measure pledging 2 times the Assessed Value of all land in the County to build New Bullards Bar Dam,”. (1961)

## Slide 15: Closing
“A society grows great when old men and women plant trees in whose shadow they shall never sit “–
Greek Proverb

## Slide 16: Questions?
October 28, 2025
Imported Water Subcommittee
24